## Schedules
Schedule - List - 101 Trenton Drive (exported on May 11, 2026)
ID # | Title | Complete | Percent Complete | Phase | Duration | Start | End | Assigned To | Accepted | Pending | Declined | Pred 1 Id | Pred 1 Type | Pred 1 Lag | Pred 2 Id | Pred 2 Type | Pred 2 Lag | Pred 3 Id | Pred 3 Type | Pred 3 Lag
1 | Put in for building permit | FALSE | 0 |  | 12 | 2025-06-18 | 2025-07-03 |  | 0 | 0 | 0
2 | Survey Excavation Pins | FALSE | 0 |  | 1 | 2025-07-04 | 2025-07-04 |  | 0 | 0 | 0 | 1 | FS | 0
3 | Excavation | FALSE | 0 |  | 1 | 2025-07-07 | 2025-07-07 |  | 0 | 0 | 0 | 2 | FS | 0
4 | Excavation Inspection. * | FALSE | 0 |  | 1 | 2025-07-08 | 2025-07-08 |  | 0 | 0 | 0 | 3 | FS | 0
5 | Footing Install | FALSE | 0 |  | 1 | 2025-07-09 | 2025-07-09 |  | 0 | 0 | 0 | 4 | FS | 0
6 | Foundation install | FALSE | 0 |  | 1 | 2025-07-10 | 2025-07-10 |  | 0 | 0 | 0 | 5 | FS | 0
7 | Foundation Prep | FALSE | 0 |  | 1 | 2025-07-14 | 2025-07-14 |  | 0 | 0 | 0 | 6 | FS | 1
8 | Call for backfill inspection | FALSE | 0 |  | 1 | 2025-07-15 | 2025-07-15 |  | 0 | 0 | 0 | 7 | FS | 0
9 | Service Connection Inspection. *48 Hou | FALSE | 0 |  | 1 | 2025-07-15 | 2025-07-15 |  | 0 | 0 | 0 | 7 | FS | 0
10 | Backfill foundation | FALSE | 0 |  | 1 | 2025-07-16 | 2025-07-16 |  | 0 | 0 | 0 | 8 | FS | 0
11 | Basement Stone | FALSE | 0 |  | 1 | 2025-07-17 | 2025-07-17 |  | 0 | 0 | 0 | 10 | FS | 0
12 | Framing | FALSE | 0 |  | 11 | 2025-07-18 | 2025-08-01 |  | 0 | 0 | 0 | 11 | FS | 0
13 | Shingles | FALSE | 0 |  | 1 | 2025-08-04 | 2025-08-04 |  | 0 | 0 | 0 | 12 | FS | 0
14 | Siding | FALSE | 0 |  | 3 | 2025-08-05 | 2025-08-07 |  | 0 | 0 | 0 | 13 | FS | 0
15 | Underslab Plumbing | FALSE | 0 |  | 2 | 2025-08-05 | 2025-08-06 |  | 0 | 0 | 0 | 12 | FS | 1
16 | Basement Poly | FALSE | 0 |  | 1 | 2025-08-08 | 2025-08-08 |  | 0 | 0 | 0 | 15 | FS | 0 | 14 | FS | 0
17 | Underslab Inspection *48 h | FALSE | 0 |  | 1 | 2025-08-11 | 2025-08-11 |  | 0 | 0 | 0 | 16 | FS | 0
18 | Basement concrete | FALSE | 0 |  | 1 | 2025-08-12 | 2025-08-12 |  | 0 | 0 | 0 | 17 | FS | 0
19 | Basement Subfloor/framing | FALSE | 0 |  | 3 | 2025-08-13 | 2025-08-15 |  | 0 | 0 | 0 | 18 | FS | 0
20 | Plumbing Rough in | FALSE | 0 |  | 4 | 2025-08-18 | 2025-08-21 |  | 0 | 0 | 0 | 19 | FS | 0
21 | HVAC rough in | FALSE | 0 |  | 2 | 2025-08-19 | 2025-08-20 |  | 0 | 0 | 0 | 19 | FS | 1
22 | Electrical rough in | FALSE | 0 |  | 6 | 2025-08-22 | 2025-08-29 |  | 0 | 0 | 0 | 19 | FS | 4
23 | Electrical Inspection | FALSE | 0 |  | 1 | 2025-09-01 | 2025-09-01 |  | 0 | 0 | 0 | 22 | FS | 0
24 | Framing Inspection. | FALSE | 0 |  | 1 | 2025-09-01 | 2025-09-01 |  | 0 | 0 | 0 | 20 | FS | 0 | 21 | FS | 0 | 22 | FS | 0
25 | Insulation Install | FALSE | 0 |  | 5 | 2025-09-02 | 2025-09-08 |  | 0 | 0 | 0 | 23 | FS | -1 | 24 | FS | 0
26 | Insulation Inspection. *48 | FALSE | 0 |  | 1 | 2025-09-09 | 2025-09-09 |  | 0 | 0 | 0 | 25 | FS | 0
27 | Drywall Install | FALSE | 0 |  | 3 | 2025-09-10 | 2025-09-12 |  | 0 | 0 | 0 | 26 | FS | 0
28 | Plaster/Prime/First Coat | FALSE | 0 |  | 15 | 2025-09-15 | 2025-10-03 |  | 0 | 0 | 0 | 27 | FS | 0
29 | Hang Doors/Window Trim | FALSE | 0 |  | 4 | 2025-10-06 | 2025-10-09 |  | 0 | 0 | 0 | 28 | FS | 0
30 | Laminate/vinyl flooring/nosing Install | FALSE | 0 |  | 4 | 2025-10-10 | 2025-10-15 |  | 0 | 0 | 0 | 29 | FS | 0
31 | Kitchen/Vanity Install | FALSE | 0 |  | 4 | 2025-10-16 | 2025-10-21 |  | 0 | 0 | 0 | 30 | FS | 0
32 | Trim Install | FALSE | 0 |  | 3 | 2025-10-22 | 2025-10-24 |  | 0 | 0 | 0 | 31 | FS | 0
33 | Plumbing finishes | FALSE | 0 |  | 2 | 2025-10-27 | 2025-10-28 |  | 0 | 0 | 0 | 32 | FS | 0
34 | Electrical Finishes | FALSE | 0 |  | 3 | 2025-10-29 | 2025-10-31 |  | 0 | 0 | 0 | 33 | FS | 0
35 | HVAC finishes | FALSE | 0 |  | 1 | 2025-10-29 | 2025-10-29 |  | 0 | 0 | 0 | 33 | FS | 0
36 | Carpet Stair | FALSE | 0 |  | 1 | 2025-11-03 | 2025-11-03 |  | 0 | 0 | 0 | 33 | FS | 0 | 34 | FS | 0 | 35 | FS | 0
37 | Handrails | FALSE | 0 |  | 2 | 2025-11-04 | 2025-11-05 |  | 0 | 0 | 0 | 36 | FS | 0
38 | Final Coat of Paint | FALSE | 0 |  | 4 | 2025-11-06 | 2025-11-11 |  | 0 | 0 | 0 | 37 | FS | 0
39 | Screen and Cranks | FALSE | 0 |  | 1 | 2025-11-06 | 2025-11-06 |  | 0 | 0 | 0 | 37 | FS | 0
40 | Final Inspection | FALSE | 0 |  | 1 | 2025-11-07 | 2025-11-07 |  | 0 | 0 | 0 | 39 | FS | 0
41 | Closing | FALSE | 0 |  | 1 | 2025-11-12 | 2025-11-12 |  | 0 | 0 | 0 | 38 | FS | 0 | 40 | FS | 2