## Sheet1
Kestrel Building Checklist
Pre Project Planning
FALSE | Get Survey and Grading Plan
FALSE | Get Electrical location from NL power
FALSE | Send above to drafter
FALSE | Take in account of sun exposure
FALSE | Make sure enough room for driveway requirement if 2 apt
FALSE | Choose windows and doors
FALSE | Look over subdivison covenants from developer and town
FALSE | Review truss drawings. Make sure all load points and girters dont fall on top of windows
FALSE | Review window lentils and beam sizing
FALSE | Review what way joists are going and minimize bulkheads
FALSE | Figure out elec panel locations
FALSE | Apply for permit
Project Planning (when permit approved)
FALSE | Order Windows and Doors
FALSE | Order Trusses
FALSE | Line up Sub contractors
FALSE | Ask plumber where to put key openings in footing
FALSE | Order siding, jblocks and plug boxes
FALSE | Order window wells
FALSE | Order Light fixtures. Use proper j blocks for lights
Site Prep
FALSE | Call surveyors for excavation pins
FALSE | Line up excavator and dig basement
FALSE | Call For excavation inspection
FALSE | Call surveyors for footing pins
FALSE | Line up footing contractor and pour footings.
FALSE |  | - Make sure footings line up with load bearing walls
FALSE |  | - Communicate any keys or notes in drawings
FALSE |  | - Verify all footings are in correct location
FALSE |  | - If footing cant be place due to frostwall, coordinate with contractor to pour footing after insulation is done and backfilled or use LVL
FALSE | Line up foundation form contractor and pour walls.
FALSE |  | - Make sure window sizes, steps ups and entrances are communicated. Verify correct sizes once completed
FALSE | Communicate with excavation contractor where service entrance is
FALSE | Get Surveyor to complete a real property report
FALSE | Knock off Tie rods and gum
FALSE | Snap chaulk lines 8-10" down, tar entire foundation
FALSE | Install frost wall insulation
FALSE |  | - Make sure its pinned up high to stop rock getting behind and cracking insulation off
FALSE | Install Window wells
FALSE | Install weeping tile
FALSE | Order stone to cover weeping tile and stone for inside foundation
FALSE | Send real property report to town inspector
FALSE | Call for backfill inspection
Framing
FALSE | Discuss with framers toilet locations to adjust floor joists if needed
FALSE | Truss uplift
FALSE |  | - Check for trusses directly above walls, if so a shiny 90 is to be installed. Insure drywall contreactor screws into those
FALSE |  | - verify any trusses less than 10-12 inches from wall are not nailed and floating
FALSE |  | - verify truss blocks are installed and that the strapping is nailed into those respectivley
FALSE |  | - verify no strapping is nailed 16 or less near a wall
FALSE | Drywall returns installed where required
FALSE | Use a square and 6 foot level to check if walls with cabinets, long walls and vanitys are plumb and square
FALSE | Install insulation, vb and plywood in panel locations
FALSE | If mold is visible on wood, spray mold-ex to remove from studs. Wear mask
FALSE
FALSE
Plumbing - Pre concrete
FALSE | Box out shower drains
FALSE | Secure water line to stay inside future wall cavity
FALSE | Secure radon pipe to stay straight
FALSE | Install drain for HRV
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
Plumbing Rough-In
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
Electrical Rough-In
FALSE | Verify
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
Hvac Rough-in
FALSE | Size up panel location
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
Post Mechanical Walkthrough
FALSE | Take video of house. Ensure ceiling and walls are pictured
FALSE | If applicable, verify garage door wiring is installed
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
Insulation and Vapour barrier
FALSE | Size up panel location
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE